# Faith Wear Apparel - Pre-Go-Live Implementation Plan
 **Target Go-Live Date:** Monday, 22 December 2025 
 **Status:** Active Implementation 
 **Days Remaining:** ~5 business days

 ---

 ## 1. CRITICAL PATH - FABRIC CONSUMPTION VALIDATION ✅ IN PROGRESS

 ### ACTION ITEM #1: Grader Fabric Consumption Confirmation
 **Owner:** Ross / Faith Wear 
 **Timeline:** ASAP (this week - by Thu 19 Dec EOD) 
 **Impact:** High - Affects BOM accuracy 
 **Status:** ⏳ Awaiting grader fabric specs

 **Task:**
 - [ ] **Contact grader** - Request fabric consumption per size:
   - S: ___ mts
   - M: ___ mts
   - L: ___ mts
   - XL: ___ mts
   - XXL: ___ mts
   - XXXL: ___ mts

 **System Validation Confirmed:** ✅
 Your current Odoo automation is **working perfectly**. Test order (Sales Order S00003) automatically:
 - ✅ Generated 4 purchase orders (Fabric, Labels, CMT, Embroidery)
 - ✅ Created 3 manufacturing orders (one per variant/color)
 - ✅ Calculated fabric consumption correctly (20 units × 1.5 mts = 30 mts per color)
 - ✅ Assigned correct fabrics to each color variant
 - ✅ Variant logic is 100% functional

 **Two Outcomes:**

 **OPTION A: Confirmed Average (1.5 mts all sizes) ✅ RECOMMENDED**
 - Current BOM stands as-is
 - System automation already validated
 - Simple to manage
 - **If accurate:** No changes needed, go live Monday

 **OPTION B: Size-Specific Consumption** (if S≠M≠L≠XL≠XXL≠XXXL)
 - **Required Change:** Create separate fabric lines in BOM by size attribute
 - **Example BOM Structure:**
   ```
   Fabric La Coste Knit Red (S) - 1.4 mts - Apply on Variants: size: Small, color: Red
   Fabric La Coste Knit Red (M) - 1.5 mts - Apply on Variants: size: Medium, color: Red
   Fabric La Coste Knit Red (L) - 1.6 mts - Apply on Variants: size: Large, color: Red
   [etc for all sizes + colors - same logic as your current color-based BOM]
   ```
 - **Effort:** 30-45 mins to update BOMs (your automation structure already proven)
 - **Accuracy:** High - true landed cost per variant
 - **Still works:** Your automation will adapt perfectly

 **DECISION REQUIRED BY:** Thursday, 19 Dec EOD
 **Action:** Get grader specs, confirm consumption pattern, update BOM if needed (quick fix if required)

 ---

 ## 2. EMBROIDERY DESIGN SPECIFICATION

 ### ACTION ITEM #2: Design/Logo Capture Process
 **Owner:** Ross / Faith Wear 
 **Timeline:** This week 
 **Impact:** Medium - Affects work order clarity

 **Current Gap:**
 - Sales order captures customer + SKU
 - BOM includes "Embroidery Service" as generic 1.00 Units
 - **Missing:** Which embroidery design goes on this specific order?

 **Solution Options:**

 **OPTION A: Custom Field on Sales Order**
 - Add field: "Embroidery Design / Logo"
 - Sales person enters: "Faith Wear Logo - Standard" or "Customer Name (Embroidered)"
 - Embroidery person sees this on work order picking list
 - **Effort:** 1 hour to set up

 **OPTION B: Link to Existing "FWA on the Go" Spreadsheet**
 - Spreadsheet already has embroidery design specs
 - Sales person references spreadsheet when creating order
 - Print design reference as note on work order
 - **Effort:** 30 mins documentation

 **OPTION C: Customer-Specific Embroidery BOM**
 - Create sub-component: "Embroidery Service - [Customer Name]"
 - More complex but fully traceable
 - **Effort:** 2 hours, only if many customer-specific logos

 **RECOMMENDATION:** Option A or B (simple, fast, adequate for launch)

 **DECISION NEEDED BY:** Thursday, 19 Dec

 ---

 ## 3. USER SETUP & TRAINING

 ### ACTION ITEM #3: Faith Wear Team Access Configuration
 **Owner:** Ross 
 **Timeline:** Wednesday-Thursday, 19-20 Dec 
 **Impact:** High - Critical for go-live

 **Users to Create:**

 | User | Role | Responsibilities | Access Level |
 |------|------|------------------|--------------|
 | **Sales Person (Name?)** | Sales User | Create sales orders, manage customer inquiries | Sales, CRM (read inventory) |
 | **Inventory Person (Name?)** | Inventory/Operations | Manage work orders, stock moves, receiving | Inventory, Manufacturing, Warehouse |
 | **Owner's Wife (Name?)** | Manager/Supervisor | Oversight, reporting, approvals | All of above + Accounting (read-only) |
 | **You (Ross)** | Technical/Admin | System maintenance, troubleshooting | Admin access (during grace period) |

 **Setup Tasks:**
 - [ ] Create user accounts in Odoo (email addresses needed)
 - [ ] Assign appropriate groups/roles
 - [ ] Test login for each user
 - [ ] Verify each can see only their relevant modules
 - [ ] Document their login credentials securely (share via secure method)

 **Training Schedule:**
 - [ ] **Thursday 19 Dec (EOD):** 30-min overview call with all three (what's changing, why Odoo matters)
 - [ ] **Friday 20 Dec (Morning):** 45-min hands-on training for Sales person (creating orders)
 - [ ] **Friday 20 Dec (Afternoon):** 45-min hands-on training for Inventory person (work orders, stock moves)
 - [ ] **Friday 20 Dec (EOD):** 15-min Q&A debrief

 ---

 ## 4. DATA CLEANUP & VALIDATION

 ### ACTION ITEM #4: System Readiness
 **Owner:** Ross 
 **Timeline:** Friday, 20 Dec 
 **Impact:** Medium - Prevents confusion on day 1

 **Tasks:**
 - [ ] **Remove all demo/test data** from the live instance
   - Delete test sales orders
   - Delete test work orders
   - Delete test inventory moves
 - [ ] **Verify opening inventory balances**
   - Current stock in WHFWA/Stock location: ___ units (confirm with Faith Wear)
   - Current stock in Subcontracting location: ___ units (goods with CMT)
   - Any stock in Pre-Production: ___ units
 - [ ] **Confirm product data**
   - 18 Golf Shirt Regular Men variants active (Red/Black/White × 6 sizes)
   - All fabric variants available (Red/Black/White La Coste)
   - Labels, CMT Service, Embroidery Service products active
 - [ ] **Set up sequence numbers** for documents
   - Sales Order: FWA-SO-001, FWA-SO-002, etc.
   - Work Order: FWA-WO-001, FWA-WO-002, etc.
 - [ ] **Verify locations are correct**
   - WHFWA/Stock (main warehouse)
   - WHFWA/Pre-Production (staging)
   - Subcontracting (with vendors)

 ---

 ## 5. DOCUMENTATION & QUICK-START GUIDES

 ### ACTION ITEM #5: Training Materials
 **Owner:** Ross 
 **Timeline:** Friday, 20 Dec 
 **Impact:** High - Reduces support calls during grace period

 **Documents to Prepare:**

 **5A. Sales Person Quick-Start Guide**
 ```
 Title: "Creating a Sales Order in Odoo - Faith Wear Apparel"

 Contents:
 1. Log into Odoo (URL, login steps)
 2. Go to Sales > Orders > Create
 3. Fill in:
    - Customer name
    - Order date
    - Product: Select variant (e.g., "Golf Shirt Regular Men (Red, M)")
    - Quantity
    - Price (auto-filled)
    - Embroidery design / Special notes (if applicable)
 4. Save & Confirm
 5. What happens next: Inventory person sees this as a manufacturing order
 6. Troubleshooting: Contact [Inventory Person] or [Ross]
 ```

 **5B. Inventory Person Quick-Start Guide**
 ```
 Title: "Managing Manufacturing Work Orders - CMT & Embroidery Workflow"

 Contents:
 1. View Manufacturing Orders
    - Go to Manufacturing > Orders
    - Filter by status "Confirmed"
 2. Pick Components for CMT
    - Click order
    - Click "Components" tab
    - Review what's needed (fabrics, labels, embroidery service)
    - Create picking slip: Click "Pick Components" button
    - Gather items from WHFWA/Stock
 3. Send to CMT
    - Once picked, create "Delivery Order" to Subcontracting location
    - Print packing list for CMT vendor
    - Record expected return date
 4. Receive from CMT
    - When goods return from CMT, create inbound receipt
    - Scan/count finished units
    - Receive into WHFWA/Stock
 5. Send to Embroidery
    - If order includes embroidery, create another work order for embroidery
    - Repeat picking/delivery/receipt process
 6. Order Complete
    - Once all processing complete, mark work order as "Done"
 7. Troubleshooting: Contact [Owner's Wife] or [Ross]
 ```

 **5C. Manager Dashboard Guide**
 ```
 Title: "Monitoring Orders & Inventory - Owner's Overview"

 Contents:
 1. Daily Health Check
    - Sales Dashboard: How many orders today? What's the pipeline?
    - Manufacturing Dashboard: How many orders in progress? Any delays?
    - Inventory Dashboard: Stock levels by location
 2. Goods in Subcontracting
    - View: Manufacturing > Orders > Filter "with subcontractor"
    - Shows: What's with CMT? Expected return date? Any overdue?
 3. Key Reports
    - Daily order summary
    - Work-in-progress report
    - Inventory by location
 4. Escalation: If something looks wrong, contact [Ross]
 ```

 **5D. Reference Document: BOM Overview**
 ```
 Title: "Understanding the Golf Shirt BOM"

 Contents:
 - Master BOM name: "Golf Shirt Regular Men (CMT)"
 - One BOM handles all 18 variants (Red/Black/White × 6 sizes)
 - How variant logic works:
   - Order for "Red, M" → Odoo pulls "Fabric La Coste Knit Red" line
   - Order for "Black, L" → Odoo pulls "Fabric La Coste Knit Black" line
 - Component breakdown:
   - Fabric (color-specific): 1.5 mts [PENDING: Verify with pattern maker]
   - Label: 1 unit
   - CMT Service: 1 unit (work center: CMT Cutting/Sewing)
   - Embroidery Service: 1 unit (work center: Embroidery)
 - What happens in manufacturing:
   - Components picked from WHFWA/Stock
   - Sent to CMT (via Subcontracting location)
   - CMT completes work
   - Goods received back to WHFWA/Stock
   - Embroidery step (if needed)
   - Final goods in stock, ready to ship
 ```

 ---

 ## 6. PRE-GO-LIVE TEST SCENARIOS

 ### ACTION ITEM #6: Full Workflow Testing
 **Owner:** Ross 
 **Timeline:** Friday-Sunday, 20-21 Dec 
 **Impact:** Critical - Catches issues before Monday

 **Test Scenario #1: Simple Order (Red Golf Shirt, M)**
 - [ ] Create sales order: "Golf Shirt Regular Men (Red, M)" × 10 units
 - [ ] Confirm order
 - [ ] Check: Does manufacturing order appear?
 - [ ] Does it pull "Fabric La Coste Knit Red" in components?
 - [ ] Create picking list → Pick fabrics + labels
 - [ ] Create delivery to CMT
 - [ ] Simulate CMT completion (manually adjust stock from Subcontracting → WHFWA/Stock)
 - [ ] Create embroidery work order
 - [ ] Complete embroidery
 - [ ] Verify finished goods back in WHFWA/Stock
 - [ ] Create delivery order to customer
 - [ ] Mark as delivered

 **Test Scenario #2: Multi-Variant Order (Black & White, Mixed Sizes)**
 - [ ] Create sales order with 3 different variants:
   - Golf Shirt Regular Men (Black, S) × 5
   - Golf Shirt Regular Men (Black, L) × 5
   - Golf Shirt Regular Men (White, M) × 10
 - [ ] Confirm order
 - [ ] Check: Does the system create picking list with correct fabrics for each variant?
 - [ ] Complete picking/CMT/embroidery workflow
 - [ ] Verify costing is accurate

 **Test Scenario #3: Inventory Location Flow**
 - [ ] Check opening inventory in WHFWA/Stock (should match Faith Wear's records)
 - [ ] After test order completion, verify:
   - Fabrics decreased from Stock
   - Temporarily in Subcontracting during CMT
   - Returned to Stock after embroidery
   - No orphaned inventory in any location

 **Document Results:**
 - [ ] All tests pass OR
 - [ ] Note any issues found + proposed fixes

 ---

 ## 7. DOMAIN CONFIGURATION (GO-LIVE READINESS)

 ### ACTION ITEM #7: Technical Setup
 **Owner:** Ross 
 **Timeline:** Friday, 20 Dec 
 **Impact:** Medium - Ensures system is stable

 **Verify:**
 - [ ] Email notifications configured (work order alerts, stock level warnings)
 - [ ] Auto-workflow triggers set up (e.g., "when order confirmed, create work order")
 - [ ] Backup scheduled (daily automated backup)
 - [ ] System time zone correct (Zimbabwe time)
 - [ ] Currency set to correct currency (USD? ZWL?)
 - [ ] Decimal places for quantities set appropriately

 ---

 ## 8. GO-LIVE CHECKLIST - MONDAY, 22 DECEMBER

 ### MORNING (Before noon handoff)

 **9:00 AM - System Health Check**
 - [ ] Log in to fwapparel.odoo.com
 - [ ] Verify all modules load
 - [ ] Confirm all user accounts active (Sales, Inventory, Manager)
 - [ ] Check no demo data present

 **9:30 AM - Team Briefing Call**
 - [ ] Call with Sales person, Inventory person, Owner's wife
 - [ ] Confirm they have login credentials
 - [ ] Everyone can access the system
 - [ ] Quick 10-min walkthrough: "This is what you'll see"

 **10:00 AM - Go-Live Official Start**
 - [ ] Announce in meeting: "Odoo is now live for Faith Wear Apparel"
 - [ ] Distribute quick-start guides
 - [ ] Clarify: "For next 30 days, Ross is here to support any issues"

 **10:30 AM - 12:00 PM - Monitor First Orders**
 - [ ] Sales person creates first test sales order
 - [ ] Inventory person confirms work order appears
 - [ ] Everyone stays online to catch issues immediately

 ### AFTERNOON (Support & Stabilization)

 **12:00 PM - 5:00 PM - On-Call Support**
 - [ ] Be available for questions/issues
 - [ ] Document any problems that arise
 - [ ] Make quick fixes as needed
 - [ ] Note any training gaps (what they struggled with?)

 **EOD - First Day Debrief**
 - [ ] Call with team: "How did it go? Any pain points?"
 - [ ] Document feedback
 - [ ] Plan adjustments for Day 2

 ---

 ## 9. 30-DAY GRACE PERIOD FOCUS AREAS

 **Week 1 (Dec 22-27):**
 - Monitor daily transactions
 - Ensure no data entry errors
 - Check inventory accuracy
 - Gather user feedback

 **Week 2-3 (Dec 28 - Jan 10):**
 - Analyze actual costing (spot-check 3-5 finished goods costs)
 - Validate subcontractor cycle times
 - Refine any workflows that aren't working smoothly
 - Plan any adjustments before paid subscription starts

 **Week 4 (Jan 11-17):**
 - Final validation of all processes
 - Prepare Faith Wear for transition to paid subscription
 - Document lessons learned for larger client implementations

 ---

 ## CRITICAL DEPENDENCIES

 **MUST BE RESOLVED BEFORE MONDAY 22 DEC:**

 | Item | Owner | Status | Due Date |
 |------|-------|--------|----------|
 | Fabric consumption by size (S-XXXL) | Ross + CMT | ⏳ Pending | Thu 19 Dec |
 | Embroidery design capture process | Ross + Faith Wear | ⏳ Pending | Thu 19 Dec |
 | User account names (Sales, Inventory, Manager) | Faith Wear | ⏳ Pending | Tue 17 Dec |
 | Opening inventory verification | Faith Wear | ⏳ Pending | Thu 19 Dec |
 | Test scenario completion | Ross | ⏳ In Progress | Sun 21 Dec |
 | Training delivery | Ross | ⏳ Scheduled | Fri 20 Dec |
 | Quick-start guides completed | Ross | ⏳ In Progress | Fri 20 Dec |

 ---

 ## SUPPORT STRUCTURE (During 30-Day Grace Period)

 **Immediate Issues (same day):**
 - Sales person can't create order → Inventory person troubleshoots
 - Inventory person → Escalate to Ross immediately

 **Non-urgent Questions:**
 - Email Ross with screenshot + description
 - Response within 24 hours

 **Weekly Check-in:**
 - Every Friday 3 PM: 30-min call with Inventory person + Manager
 - Review what happened that week
 - Plan next week

 **Emergency Contact:**
 - Ross contact: [phone/email to be confirmed]

 ---

 ## SUCCESS METRICS - END OF 30 DAYS

 **By January 17, 2026, FWA go-live is successful if:**

 ✅ **Operational Metrics:**
 - 50+ sales orders created and processed
 - 100% of orders followed correct workflow (picking → CMT → embroidery → delivery)
 - Zero inventory discrepancies between Odoo and physical count
 - Zero data entry errors causing problems

 ✅ **User Adoption:**
 - Sales person comfortable creating orders independently
 - Inventory person managing work orders without assistance
 - Manager can run basic reports

 ✅ **Business Metrics:**
 - Costing accuracy verified (spot-checked 5 finished goods)
 - CMT turnaround times tracked in Odoo
 - Customer delivery dates met
 - No complaints about system usability

 ✅ **System Stability:**
 - Zero unplanned downtime
 - All backup/recovery procedures tested
 - No data corruption or loss

 ---

 ## NOTES & ASSUMPTIONS

 1. **Fabric Consumption:** Currently assuming 1.5 mts across all sizes (pending pattern maker verification)
 2. **Embroidery Designs:** Assuming design specs come from "FWA on the Go" spreadsheet (to be formalized)
 3. **User Training:** Assuming Faith Wear team has basic computer literacy
 4. **Go-Live Date:** Monday 22 Dec is feasible IF fabric consumption is confirmed by Thu 19 Dec
 5. **Scope:** Golf Shirts (CMT + Embroidery) only. T-Shirt printing BOM to be added later if needed.

 ---

 ## FINAL PRE-GO-LIVE CHECKLIST - READY FOR MONDAY 22 DECEMBER

 ### THIS WEEK (By Friday 20 Dec)

 **CRITICAL PATH:**
 - [ ] **Get fabric specs from grader** (S through XXXL consumption) - **DUE THU 19 DEC EOD**
 - [ ] **Confirm 1.5 mts is correct** OR identify size-specific requirements
 - [ ] **Update BOM if needed** (30 mins if size-specific changes required)

 **USER SETUP:**
 - [ ] **Get names & email addresses:**
   - Sales person: ________________
   - Inventory person: ________________
   - Owner's wife (manager): ________________
 - [ ] **Create user accounts in Odoo** (all three)
 - [ ] **Assign roles/groups** (Sales, Inventory/Operations, Manager)
 - [ ] **Test logins** (each user verifies they can access system)

 **DATA VALIDATION:**
 - [ ] **Verify opening inventory** (compare to current warehouse counts)
 - [ ] **Confirm all products active** (18 Golf Shirt variants + materials)
 - [ ] **Remove all demo/test data** from live instance
 - [ ] **Test full workflow** (sales order → POs → MOs → completion)

 **TRAINING & DOCUMENTATION:**
 - [ ] **Fri 20 Dec:** Team training (3 sessions, 2 hours total)
 - [ ] **Quick-start guides** finalized and printed (4 documents)
 - [ ] **Emergency contact info** ready

 **SYSTEM READY:**
 - [ ] **Email notifications** configured
 - [ ] **Backup scheduled** (daily)
 - [ ] **Time zone** Zimbabwe
 - [ ] **Currency** verified

 ---

 ### MONDAY 22 DECEMBER - GO-LIVE

 **9:00 AM:** System health check 
 **9:30 AM:** Team briefing (15 mins) 
 **10:00 AM:** LIVE 
 **10:30 AM-12:00 PM:** Live monitoring 
 **12:00 PM-5:00 PM:** On-call support 
 **5:00 PM:** First day debrief

 ---

 ### 30-DAY GRACE PERIOD

 **Week 1:** Stabilization + daily monitoring 
 **Week 2-3:** Validation + costing verification 
 **Week 4:** Preparation for paid subscription 

 **Success Metrics:**
 - ✅ 50+ orders processed
 - ✅ 100% workflow compliance
 - ✅ Zero inventory discrepancies
 - ✅ Users comfortable independently
 - ✅ System stability confirmed

 ---

 **Document prepared by:** AI Implementation Assistant 
 **Last updated:** 18 December 2025 
 **Final review:** Thursday 19 Dec EOD (after grader fabric confirmation)
 **Status:** READY FOR GO-LIVE MONDAY 22 DECEMBER